Thrive | Confidential

Clearstead Infrastructure Consolidation

Technical Implementation Plan

Table of Contents

1

Purpose	6

Executive Summary	6

Revision History	7

Implementation Summary	8

Assumptions	8

Timeline of Phases	9

Phase 1 – M365 Security Assessment Remediation	10

Requirements/Prerequisites	10

Approximate Timing	10

Implementation Details	10

Current State Overview	10

Change Summary for Future State	10

Risks and Mitigations	10

Testing and Verification	12

Next Day Support	12

Phase 2 – Clarius M365 Migration	13

Requirements/Prerequisites	13

Approximate Timing	13

Implementation Details	13

Current State Overview	13

Change Summary for Future State	13

Data Cleanup/Archival	13

Exchange Online Migration	13

Microsoft Teams Migration	14

Sharepoint Online and OneDrive Migration	14

Risks and Mitigations	14

Testing and Verification	15

Next Day Support	16

Phase 3 – Clarius Workstation Entra Migration to Clearstead HQ And Server Decommissioning	17

Requirements/Prerequisites	17

Approximate Timing	17

Implementation Details	17

Current State Overview	17

Change Summary for Future State	17

Vasion Print Deployment (aka Printer Logic)	17

Workstation Entra Migrations	17

Risks and Mitigations	18

Testing and Verification	19

Next Day Support	20

Phase 4 – Clearstead HQ Server Decommissioning	21

Requirements/Prerequisites	21

Approximate Timing	21

Implementation Details	21

Current State Overview	21

Change Summary for Future State	21

Legacy Server Decommissions	21

Risks and Mitigations	22

Testing and Verification	22

Next Day Support	23

Phase 5 – Clearstead Trust M365 Migration	24

Requirements/Prerequisites	24

Approximate Timing	24

Implementation Details	24

Current State Overview	24

Change Summary for Future State	24

Data Cleanup/Archival	24

Exchange Online Migration	24

Sharepoint Online Migration	25

Microsoft Teams Migration	26

Risks and Mitigations	26

Testing and Verification	27

Next Day Support	28

Phase 6 – Clearstead Trust Workstation Entra Migration to Clearstead HQ	29

Requirements/Prerequisites	29

Approximate Timing	29

Implementation Details	29

Current State Overview	29

Change Summary for Future State	29

Workstation Migrations	29

Risks and Mitigations	30

Testing and Verification	31

Next Day Support	31

Phase 7 – Clearstead Trust Server and Win11 virtual workstation Decommissioning	33

Requirements/Prerequisites	33

Approximate Timing	33

Implementation Details	33

Current State Overview	33

Change Summary for Future State	33

Server Decommissions	33

Risks and Mitigations	34

Testing and Verification	35

Next Day Support	35

Phase 8 – Clearstead Avalon Trust Server Migration to Clearstead HQ and Virtual Workstation Decommissioning	37

Requirements/Prerequisites	37

Approximate Timing	37

Implementation Details	37

Current State Overview	37

Change Summary for Future State	37

Windows 11 Virtual Workstation Decommissioning	37

Server Migrations	38

Risks and Mitigations	38

Testing and Verification	39

Next Day Support	39

Phase 9 – Clearstead Avalon Trust Workstation Hybrid AD Migration to HQ	40

Requirements/Prerequisites	40

Approximate Timing	40

Implementation Details	40

Current State Overview	40

Change Summary for Future State	40

Workstation Migrations	40

Windows 11 Virtual Workstations	40

Server Migrations	41

Risks and Mitigations	41

Testing and Verification	43

Next Day Support	43

Phase 10 –Clearstead Avalon Trust M365 Migration	45

Requirements/Prerequisites	45

Approximate Timing	45

Implementation Details	45

Current State Overview	45

Change Summary for Future State	45

Data Cleanup/Archival	45

Exchange Online Migration	45

Microsoft Teams Migration	46

Sharepoint Online and OneDrive Migration	46

Risks and Mitigations	46

Testing and Verification	47

Next Day Support	48

Phase 11 – Clearstead Advisory SOlutions Server AD Migration and Workstation Hybrid AD Migration to Clearstead HQ	49

Requirements/Prerequisites	49

Approximate Timing	49

Implementation Details	49

Current State Overview	49

Change Summary for Future State	50

Active Directory Server and Virtual Workstation Migration	50

Risks and Mitigations	52

Testing and Verification	54

Next Day Support	54

Phase 12 – Clearstead Advisory SOlutions Workstation Hybrid Migrations To ClearStead HQ	56

Requirements/Prerequisites	56

Approximate Timing	56

Implementation Details	56

Current State Overview	56

Change Summary for Future State	56

Workstation Migrations	56

Risks and Mitigations	56

Testing and Verification	58

Next Day Support	59

Phase 13 – Clearstead Advisory Solutions Server Decommissioning	60

Requirements/Prerequisites	60

Approximate Timing	60

Implementation Details	60

Current State Overview	60

Change Summary for Future State	61

Server Decommissions	61

Hyper-V DR Replication	62

Risks and Mitigations	63

Testing and Verification	63

Next Day Support	63

Acceptance Criteria	65

Deliverables	65

Document End	66

# Purpose

The purpose of this document is to detail, at a high level, the recommended path forward as it relates to Clearstead’s network and server infrastructure and ensure that all devices, dependencies, configurations, and systems pertaining to and/or affecting the scope of this project are properly detailed.  Most importantly it is to ensure proper procedures are taken to control project scope and avoid wasted effort both for Thrive and our customers.

By executing this document, you verify that expectations of your to-be-implemented environment or changes thereof have been properly scoped and designed by Thrive. This implementation plan details the steps required to complete the various phases of the project. Other important planning details outlined include the associated risks, downtime, and rollback plans for each individual phase of the project.

This is a living document and is subject to changes as further deep-dive discovery, discussion and work occurs.

# Executive Summary

Clearstead Advisors, LLC is a wealth management firm headquartered in Cleveland, Ohio with 350-400 employees across 11 locations – the firm is currently split into five entities:

- Clearstead (aka HQ or “Clearstead proper”)

- Clearstead Trust

- Clearstead Avalon Trust

- Clearstead Advisory Solutions

- Clarius

Currently, each division is managed by a separate Managed Service Provider with different technology stacks.  Clearstead has retained Thrive to be their single managed services provider and consolidate into one cohesive technology stack.

Thrive has reviewed Clearstead’s server infrastructure at a high level.  We also participated in various meetings to understand the business goals and requirements as they relate to technology.

# Revision History

| Rev # | Author(s) | Change | Date |
| --- | --- | --- | --- |
| 1.0 | Toni Coscarelli | Initial Document | 3/24/2026 |

# Implementation Summary

Clearstead has requested a consolidation of infrastructure into the Cleveland HQ environment.  This will occur via a series of efforts to merge M365 tenants, Active Directory workstation and server migrations, server and workstation decommissioning, and file migrations to Egnyte.

Assumptions

- Clearstead Trust server decommissioning plan assumes all file server data has been moved to Egynte.

- Client to coordinate any necessary support and migration assistance for 3rd party applications during integration activities.

- Clearstead reports to Thrive that Clearstead Advisory Services Exchange, SharePoint, and Teams data has been previously migrated and therefore is not in scope.

- Thrive security and management tools have been rolled out as part of onboarding and as such are not in scope of this Technical Implementation Plan.

# Timeline of Phases

The below is a potential timeline of phases, meant to represent overlapping project priorities and prerequisites. Dates are approximate. The greatest level of variability in timeline phases will depend on customer-driven decisions. All timeline items are subject to change based on real-world business impact.

| Phase | Description | Est. Duration | Dependencies | Notes |
| --- | --- | --- | --- | --- |
| Phase 1 | M365 Security Assessment Remediation | 2 Weeks | SOW Signed |  |
| Phase 2 | Clarius M365 Migration | 4 Weeks | Phase 1 Complete Phase 3 Concurrent |  |
| Phase 3 | Clarius Workstation Migration to Entra | 3 Weeks | Phase 1 Complete Phase 2 Concurrent |  |
| Phase 4 | Clearstead HQ Server Decommissioning | 3 Weeks |  |  |
| Phase 5 | Clearstead Trust M365 Migration | 4 Weeks | Phase 1 Complete Phase 6 Concurrent |  |
| Phase 6 | Clearstead Trust Workstation Migration to Entra | 3 Weeks | Phase 5 Concurrent |  |
| Phase 7 | Clearstead Trust Server and Win11 Virtual Workstation Decommissioning | 3 Weeks | Phases 5 & 6 Complete |  |
| Phase 8 | Clearstead Avalon Trust Server Migration to Clearstead HQ and Virtual Workstation Decommissioning | 4 Weeks | Phase 9 Concurrent Phase 10 Concurrent |  |
| Phase 9 | Clearstead Avalon Trust Workstation Hybrid AD Migration to HQ | 4 Weeks | Phase 1 Complete Phase 8 Concurrent Phase 10 Concurrent |  |
| Phase 10 | Clearstead Avalon Trust M365 Migration | 4 Weeks | Phase 1 Complete Phase 9 Concurrent Phase 8 Concurrent |  |
| Phase 11 | Clearstead Advisory Solutions Server AD Migration and Virtual Workstation Hybrid AD Migration to Clearstead HQ | 4 Weeks | Phase 12 Concurrent |  |
| Phase 12 | Clearstead Advisory Solutions Workstation Migrations To Clearstead HQ | 3 Weeks | Phase 11 Concurrent |  |
| Phase 13 | Clearstead Advisory Solutions Server Decommissioning | 3 Weeks | Phase 11 Complete Phase 12 Complete |  |

# Phase 1 – M365 Security Assessment Remediation

## Requirements/Prerequisites

- Signed and Executed Statement of Work

## Approximate Timing

This phase is expected to take 2 weeks.  Thrive recommends this work be completed prior to all other phases detailed in this plan.

## Implementation Details

Current State Overview

The Clearstead HQ tenant is the destination tenant for Clearstead Trust, Clearstead Avalon Trust and Clarius.  Clearstead Advisory Solutions was migrated to the Clearstead HQ tenant prior to Thrive’s engagement.

Change Summary for Future State

Thrive has completed an M365 Security Assessment led by Jason Lisnak.  The Clearstead IT team has reviewed the findings and has collaborated with Thrive on the best approach forward.  Items identified for remediation are detailed on the “Clearstead – M365 Security Check.xlsx” document, of which the master copy resides with Dennis Kasper.  Thrive will execute these changes to mitigate identified gaps and secure the Clearstead HQ M365 environment.

## Risks and Mitigations

| Risk | Likelihood | Mitigation Strategy | Rollback Plan |
| --- | --- | --- | --- |
| User productivity disruption (access blocks, extra prompts). Examples are policies that affect Conditional Access, MFA, device compliance, and session controls which can block legitimate users (travel, new devices, special roles) and increase authentication friction. | Medium | Roll out in phases where possible. Maintain break-glass accounts (cloud-only, excluded from CA, long/strong creds, monitored). Communicate changes, provide quick “How to enroll device / fix sign-in” guides. | Revert settings to original. |
| Legacy authentication / SMTP / old apps break - Disabling legacy auth or Authenticated SMTP can disrupt scanners, line-of-business apps, older Office clients, and integrations. | Medium | Identify usage via Entra sign-in logs and message trace before enforcement. Replace with modern auth options (OAuth, Graph API, application permissions, connector-based relay). For email devices: use Direct Send, SMTP relay, or approved third-party send services with proper auth. | Revert settings to original. |
| Overblocking email (false positives, quarantines) - Tightening anti-phish/anti-spam policies (quarantine actions, attachment filtering, external tagging) can cause business-impacting missed emails. | Medium | Track metrics: false positive rate, time-to-release, top blocked senders. | Revert settings to original. |
| Misconfiguration risk (locking out admins or blocking critical services) - Conditional Access or tenant-wide policy misconfig can cause widespread outages or admin lockout. | Low | Use change windows and roll-back plans. Keep break-glass accounts tested and monitored. Use named locations, exclusions, and staged rollout with pilot groups. | Revert settings to original. |
| Third-party/vendor access friction (partners, guests, B2B) - Tight guest controls, MFA requirements, and session restrictions can disrupt vendor workflows. | Low | Ensure all vendor access is reviewed and understood in advance of changes. | Revert settings to original. |
| Licensing and cost expansion - Some recommended controls (Defender suite, Cloud Apps, PIM, advanced auditing) may require additional licensing or SKUs; costs can rise. | Low | Map controls to license requirements and confirm coverage before rollout. Prioritize “highest risk reduction per dollar” controls first. Track security improvements vs. cost and business outcomes. | Revert settings to original. |
| Business continuity risks (incident response assumptions change) - New controls change the “shape” of incidents and existing IR playbooks may not match. | Low | Update IR playbooks: compromised account, BEC, ransomware, malicious inbox rules, risky OAuth app, etc. Run tabletop exercises after major changes. | Revert settings to original. |

## Testing and Verification

Identified changes are numerous and listing each here with testing and verification steps would be cumbersome.  Testing of changes will happen as changes are made, with test steps specific to the change made communicated to the Clearstead team and/or performed by a Thrive engineer.  Thrive and Clearstead will identify pilot groups where possible as well as individual users for collaboration on configuration changes.

## Next Day Support

Next Day Support Strategy:

- Support Type: Remote
- Thrive Resource(s): Thrive project engineers, Thrive pod
- Coverage Hours: Support bridge for immediate NDS as appropriate, subsequent times per pod via support tickets
- Customer Contact: Ed Mielcarek

# Phase 2 – Clarius M365 Migration

## Requirements/Prerequisites

- Signed and Executed Statement of Work

- Completion of Phase 1

- This phase will run concurrent with Phase 3

## Approximate Timing

This phase is expected to take approximately 4 weeks from start to finish.

## Implementation Details

Current State Overview

Clarius is the newest acquisition to the Clearstead organization at the time of this writing.  Clarius has minimal premise infrastructure, with only a single workstation serving as a phone system management platform.

Clarius has three virtual servers in Microsoft Azure, two domain controllers (CLA-AZW2-DC1 and CLA-AZWC-DC2), and one file server (APOLLO2).  APOLLO2 was previously used to house Quickbooks files, but a migration/solution change to RightWorks occurred previously.  Legacy Quickbooks data exists in T:\DataShares\Quickbooks.  

Clarius has an M365 tenant that contains approximately 55 users for use of email, Teams and other M365 apps.

Change Summary for Future State

Clarius’s M365 environment that will be migrated to the Clearstead HQ tenant.

Data Cleanup/Archival

In advance of any M365 work as described below, it is recommended that a data cleanup/archival task be completed, led by the Clearstead IT team.  This will ensure that old and unused legacy data is not carried forward into Egnyte or from M365 tenant to tenant.

Exchange Online Migration

An M365 migration will be executed, with mailboxes and associated assets being moved to the Clearstead tenant.  There are currently approximately 55 user and 14 shared mailboxes within the Clarius tenant.  There are one hundred 365 groups, one hundred distribution lists, a single dynamic distribution list and 5 mail-enabled security groups that will be migrated.  There are 6 resource mailboxes and 120 contacts to migrate.

There are 34 Exchange transport rules to migrate.

One public folder mailbox exists containing one public folder with zero items.

M365 licensing is a wide mix of Business Premium, E1, E3 and E5.

The third-party email security solutions Inky, Global Relay and Echoworx are in use.  There are multiple email connectors for various purposes.

Accepted domains consist of the following:

- clariusgroup.com (default domain)

- theclariusgroup.com

- stillwatercreekvineyard.com

- clariusgroup.onmicrosoft.com

- clariusgroup.mail.onmicrosoft.com

- 3hbmx516umd5kuwrdhstk7.client.inkyphishfence.com

Any MTO currently in place will be torn down 7-14 days prior to the start of work for this migration, as mailboxes will be required to be created for the users as a target for the source tenant.

Microsoft Teams Migration

Teams is in use with a significant number of channels in existence.  Thrive consult with the Clearstead team to identify channels to migrate.

Sharepoint Online and OneDrive Migration

A total of 34 Sharepoint Online sites exist with files totaling around 60GB.  These will be migrated to Egnyte.

Approximately 47 users have files in OneDrive totaling about 1.4TB (with one user having over 1TB).  These will be migrated to Egnyte.

## Risks and Mitigations

| Risk | Likelihood | Mitigation Strategy | Rollback Plan |
| --- | --- | --- | --- |
| Identity Mismatch / Login Failures - Users can’t log in, duplicate accounts appear, or SSO breaks due to mismatched UPNs or other account settings. | Medium | Validate authentication with a pilot group. | Abort migration and remain in source tenant. |
| Mail Flow Disruption - Emails bounce, disappear, or route incorrectly. | Low | Lower DNS TTL in advance, validate connectors and routing rules, and perform cutover testing as detailed below. | Abort migration and remain in source tenant. |
| File Access/Availability Issues - Mailboxes, OneDrive, or SharePoint data fails to fully migrate, or items are skipped without visibility. | Low | Run pre-migration assessments, use reputable migration tools, review error reports in detail, and perform post-migration validation as detailed below. | Abort migration and remain in source tenant. |
| Outlook & Client Issues - Users get constant password prompts, Outlook profiles break, or Autodiscover points to the wrong tenant. | Low | Plan for Outlook profile rebuild or use tools/scripts to reset same, clear cached credentials, and ensure DNS/Autodiscover cutover is tightly coordinated. | Abort migration and remain in source tenant. |
| Application & SSO Failures - Line-of-business apps and third-party integrations stop working due to tenant change or missing enterprise app configs. | Low | Inventory all applications using Azure AD, reconfigure enterprise apps in target tenant, test SSO thoroughly, and validate SCIM/provisioning where used. | Abort migration and remain in source tenant. |
| Teams & Collaboration Gaps - Loss of chat history, broken Teams memberships, missing files, or degraded collaboration experience. | Medium | Set expectations (chat history often limited), use specialized migration tools for Teams, recreate teams and memberships, and validate access to underlying SharePoint data. | Abort migration and remain in source tenant. |
| Licensing & Feature Gaps - Users lose access to features due to incorrect or missing license assignments in the new tenant. | Low | Map licenses ahead of time, assign before user cutover, and validate service availability (Exchange, Teams, etc.). | Abort migration and remain in source tenant. |
| Conditional Access / Security Policy Conflicts - Users get blocked by Conditional Access, MFA loops, or device compliance issues. | Medium | Review and stage Conditional Access policies, test with pilot users, and temporarily relax policies during migration if necessary. | Abort migration and remain in source tenant. |
| DNS Cutover Timing Issues - Improper timing causes downtime, mail routing issues, or service interruptions. | Low | Lower DNS Time-To-Live (TTL) well in advance, schedule cutover during low usage, and validate DNS changes immediately after cutover. | Abort migration and remain in source tenant. |
| User Confusion & Support Overload - Even if everything technically works, users flood support because things look different or require new logins. | Medium | Communicate clearly, provide quick-start guides, run pilot groups, and have hypercare support ready post-cutover. | N/A |

## Testing and Verification

The following data points will be used to verify a successful migration:

- User able to login to https://portal.office.com

- User able to open Outlook, send and receive email

- User able to view and create calendar invites

- User able to open Egnyte public and private folders

- User able to open and use Teams as expected

- User able to use Outlook on mobile device

## Next Day Support

Next Day Support Strategy:

- Support Type: Onsite & Remote
- Thrive Resource(s): Thrive project engineers, Thrive pod 
- Coverage Hours: Support bridge for immediate NDS, subsequent times per pod via support tickets
- Customer Contact: Ed Mielcarek

# Phase 3 – Clarius Workstation Entra Migration to Clearstead HQ And Server Decommissioning

## Requirements/Prerequisites

- Signed and Executed Statement of Work

- Completion of Phase 1

- This phase will run concurrent to Phase 2

## Approximate Timing

This phase is expected to take approximately 3 weeks from start to finish.

## Implementation Details

Current State Overview

Clarius is the newest acquisition to the Clearstead organization at the time of this writing.  Clarius has minimal premise infrastructure, with only a single workstation serving as a phone system management platform.

Clarius has three virtual servers in Microsoft Azure, two domain controllers (CLA-AZW2-DC1 and CLA-AZWC-DC2), and one file server (APOLLO2).  APOLLO2 was previously used to house Quickbooks files, but a migration/solution change to RightWorks occurred previously.  Legacy Quickbooks data exists in T:\DataShares\Quickbooks.

Clarius has an M365 tenant that contains approximately 55 users for use of email, Teams and other M365 apps.

Change Summary for Future State

Vasion Print will be implemented for printer usage and management.  Workstations will be migrated to Clearstead HQ Entra.

Azure servers will be decommissioned at the conclusion of Phases 2 and 3.

Vasion Print Deployment (aka Printer Logic)

Vasion Print will be deployed for 8 printers.

Workstation Entra Migrations

Workstations will be migrated to Clearstead Entra.  The high-level process for this is as follows:

- Ensure a local admin account is known and accessible

- Ensure the applicable Clarius user has a Clearstead AD/Entra account

- Unjoin the workstation from the Clarius AD

- Join the workstation to Clearstead Entra

- Sign in as the user

- Migrate the relevant files from the Clarius AD profile to the newly created profile for the user

Note that Thrive will try to script Entra migrations.  In the event it doesn't work, it will be necessary to Entra join manually with user assistance, approximately 1 hour per machine.


Aure Server Decommissioning

Once the entirety of work has been completed in phases 2 and 3, the Azure servers will be decommissioned.

## Risks and Mitigations

| Risk | Likelihood | Mitigation Strategy | Rollback Plan |
| --- | --- | --- | --- |
| User Profile Loss / New Profile Creation - Users log in post-migration and get a fresh profile - desktop empty, apps reset, Outlook signatures gone. | Low | Use profile migration tools and test profile continuity with pilot users before broad rollout. | Rejoin devices to Clarius AD. |
| Application Authentication Breakage - Apps tied to old domain credentials stop working (line-of-business apps, mapped drives, legacy auth apps). | Low | Inventory all apps beforehand, reconfigure apps for Entra ID, and test critical apps with pilot users. | Rejoin devices to Clarius AD. |
| Loss of Access to Network Resources - Users can’t access files, printers, or internal apps still tied to the old domain. | Medium | Migrate resources to cloud (Egnyte) or implement hybrid access. Clearly define what is being decommissioned vs. retained and where the new data lives via user comms. | Rejoin devices to Clarius AD. |
| Device Join / Enrollment Failures - Devices fail to join Microsoft Entra ID or enroll in Microsoft Intune, leaving them unmanaged. | Low | Validate join/enrollment process, ensure licensing is correct, and test across device types. | Rejoin devices to Clarius AD. |
| Conditional Access & Compliance Lockouts - Devices or users get blocked immediately after migration due to Conditional Access or compliance policies. | Low | Stage policies in report-only mode first, exclude pilot users, and gradually enforce policies after confirming device compliance. | Rejoin devices to Clarius AD. |
| GPO Loss / Configuration Drift - All Group Policy Objects disappear, and machines lose security settings, mapped drives, and configurations. | Low | Translate GPOs into Intune configuration profiles, compliance policies, and scripts. | Rejoin devices to Clarius AD. |
| Printer & Drive Mapping Failures - mapped drives and printers vanish, and users suddenly forget how to function. | Low | Ensure exhaustive end user comms. | N/A |
| Remote User Disruption - Remote users can’t authenticate or complete the migration because they’re off-network. | Medium | Use remote-friendly migration methods, ensure internet-based access to required services, and provide clear instructions. Alternatively, require user device to be in-office during migration. | Rejoin devices to Clarius AD. |
| User Experience Shock (a.k.a. “Everything Looks Different”) - Even if technically successful, users struggle with new login format, missing resources, or changed workflows. | High | Communicate clearly with exhaustive comms and run a pilot group to identify pain points before full rollout. | N/A |

## Testing and Verification

The following data points will serve to confirm a successful migration:

- Device is present in Entra

- Device shows Compliant in Intune, policies applied

- Primary user is correctly assigned

- User is able to login successfully with MFA prompts

- User expected items (desktop, documents, etc) are present

- Egnyte is usable

- Expected applications open and function

- Outlook is connected to mailbox and shows expected data

- Teams is connected and usable

- Printers are as expected and usable

- VPN profile is usable, if applicable

## Next Day Support

Next Day Support Strategy:

- Support Type: Onsite & Remote
- Thrive Resource(s): Thrive project engineers, Thrive pod
- Coverage Hours: 2 Support bridge for immediate NDS, subsequent times per pod via support tickets
- Customer Contact: Ed Mielcarek

# Phase 4 – Clearstead HQ Server Decommissioning

## Requirements/Prerequisites

- Signed and Executed Statement of Work

## Approximate Timing

This phase is expected to take approximately 3 weeks from start to finish.

## Implementation Details

Current State Overview

The Clearstead HQ site is home to a two host VMware HA cluster utilizing an HPE MSA 2050 SAN for shared storage.  It has an Active Directory environment consisting of two domain controllers (CS-DC-01 and CS-DC-02).  This AD environment will be the target for the AD migrations for the below integrated entities.  Clearstead HQ is also the federated source for the hybrid Clearstead M365 Entra tenant, which likewise will be the target tenant for Clearstead Trust and Clearstead Avalon Trust M365 migrations.

Change Summary for Future State

While no servers at HQ will be migrated elsewhere, a number of them have been identified as targets for decommission in an email from Dragana Vujovic to Matt Stevens on Nov 6, 2025.  Thrive will decommission these servers.

Legacy Server Decommissions

The following servers will be decommissioned:

- CS-APP-02 was used for Fidelity Wealthscape, Sage 50, Actian Zen, and PDF/Xchang.  These applications are legacy and this server will be decommissioned.

- CS-APP-03 was used for an “old Salesforce-like test server” and will be decommissioned.

- CS-APP-04 was used for Paessler and PRTG and will be decommissioned as these applications have been replaced by Thrive toolsets.

- CS-DB-01 is noted as having been used as a SQL server for VMware Horizon View, which is no longer in production.  This server will be decommissioned.

- CS-IMG-01 is noted as a legacy PDQ Deploy/Inventory application server and will be decommissioned.

- CS-WKS-01 is noted as an “administrative workstation” and will be decommissioned.

- CS-WKS-02 is noted as an “administrative workstation” and will be decommissioned.

- CS-WKS-03 is noted as an “administrative workstation” and will be decommissioned.

- AW-VSCANNER-01 is a legacy Arctic Wolf server, replaced by Thrive toolsets, and will be decommissioned.

All servers will be shut down for several days to a week prior to decommissioning to ensure no unintended impacts.  Backups/archival copies will be taken of critical servers where concern exists for data compliance or long-term possible need.

## Risks and Mitigations

| Risk | Likelihood | Mitigation Strategy | Rollback Plan |
| --- | --- | --- | --- |
| Server still in use by users, processes or workflows. | Medium | Identify server role(s) and installed applications. Confirm no active users or business processes rely on servers. Notify application owners and business stakeholders. Obtain formal approval to decommission. Confirm replacement systems (if applicable) are fully operational. | Turn server back on. |

## Testing and Verification

The following data points will serve to confirm a successful decommission of each server:

- Last backup is successful and present

- Server is removed from domain, AD object not present

- Internal DNS records for server removed

- Connectivity to replacement system, if applicable, is verified

- Server is removed from monitoring tools

- Documentation is updated reflecting removal of server

## Next Day Support

Next Day Support Strategy:

- Support Type: Remote
- Thrive Resource(s): Thrive project engineers, Thrive pod 
- Coverage Hours: Support bridge for immediate NDS, subsequent times per pod via support tickets
- Customer Contact: Ed Mielcarek

# Phase 5 – Clearstead Trust M365 Migration

## Requirements/Prerequisites

- Signed and Executed Statement of Work

- Completion of Phase 1

- This phase will run concurrent with Phase 6

## Approximate Timing

This phase is expected to take approximately 4 weeks from start to finish.

## Implementation Details

Current State Overview

Clearstead Trust has a dedicated Active Directory environment running on a two host VMware HA cluster with a NetApp SAN as shared storage.  This currently consists of two domain controllers (CSTRUST-AD1 and CSTRUST-AD2), a file server (CSTRUST-FILE), and a server used for PowerChute Network Shutdown (CSTRUST-PCNS).  Additionally, VM’s exist for Arctic Wolf (replaced during onboarding) and Zerto.  There are approximately 21 workstations joined to the Clearstead Trust Active Directory.

Change Summary for Future State

Clearstead Trust has a dedicated M365 environment that will be migrated to the Clearstead HQ tenant.

Data Cleanup/Archival

In advance of any M365 work as described below, it is recommended that a data cleanup/archival task be completed, led by the Clearstead IT team.  This will ensure that old and unused legacy data is not carried forward into Egnyte or from M365 tenant to tenant.

Exchange Online Migration

An M365 migration will be executed in conjunction with the above Entra migration, with mailboxes and associated assets being moved to the Clearstead tenant.  There are currently approximately 22 licensed mailboxes and 21 shared mailboxes within the Clearstead Trust tenant.

There are seven 365 groups, eleven distribution lists, no dynamic distribution lists and no mail-enabled security groups that will be migrated.  There are 4 resource mailboxes (with 2 being named “DO NOT USE”) and 60 contacts to migrate.

There are 14 Exchange transport rules to migrate.

One public folder mailbox exists containing one public folder with zero items.

M365 licensing is a mix of Business Premium and Exchange Online (Plan 1) licenses.  For reference, there are 21 Business Premium licenses currently unused.

The third-party email security solutions Proofpoint and Zix are in use.  There are multiple email connectors for various purposes.

Accepted domains consist of the following:

- clearsteadtrust.com (default domain)

- plimsollmarkcapital.com

- atlantictrustmaine.com

- afsofmaine.com

- afsofmaine.onmicrosoft.com

- afsofmaine.mail.onmicrosoft.com

Any MTO currently in place will be torn down 7-14 days prior to the start of work for this migration, as mailboxes will be required to be created for the users as a target for the source tenant.

SSO for Fi-Tek will be reconfigured to point to the Clearstead tenant.

Sharepoint Online Migration

A total of 18 Sharepoint Online active sites exist with a total of less than 1GB of space used.  A quick analysis of the files shows that most are old and likely abandoned.  Nonetheless, these files should be reviewed for possible migration to the Clearstead Egnyte storage platform.  If necessary, these files can be quickly migrated manually.

Microsoft Teams Migration

Teams is in use, configured on a minimal basis, with only 2 channels in use.  Thrive will migrate these teams and channels to the Clearstead tenant if desired.

## Risks and Mitigations

| Risk | Likelihood | Mitigation Strategy | Rollback Plan |
| --- | --- | --- | --- |
| Identity Mismatch / Login Failures - Users can’t log in, duplicate accounts appear, or SSO breaks due to mismatched UPNs or other account settings. | Medium | Validate authentication with a pilot group. | Abort migration and remain in source tenant. |
| Mail Flow Disruption - Emails bounce, disappear, or route incorrectly. | Low | Lower DNS TTL in advance, validate connectors and routing rules, and perform cutover testing as detailed below. | Abort migration and remain in source tenant. |
| File Access/Availability Issues - Mailboxes, OneDrive, or SharePoint data fails to fully migrate, or items are skipped without visibility. | Low | Run pre-migration assessments, use reputable migration tools, review error reports in detail, and perform post-migration validation as detailed below. | Abort migration and remain in source tenant. |
| Outlook & Client Issues - Users get constant password prompts, Outlook profiles break, or Autodiscover points to the wrong tenant. | Low | Plan for Outlook profile rebuild or use tools/scripts to reset same, clear cached credentials, and ensure DNS/Autodiscover cutover is tightly coordinated. | Abort migration and remain in source tenant. |
| Application & SSO Failures - Line-of-business apps and third-party integrations stop working due to tenant change or missing enterprise app configs. | Low | Inventory all applications using Azure AD, reconfigure enterprise apps in target tenant, test SSO thoroughly, and validate SCIM/provisioning where used. | Abort migration and remain in source tenant. |
| Teams & Collaboration Gaps - Loss of chat history, broken Teams memberships, missing files, or degraded collaboration experience. | Medium | Set expectations (chat history often limited), use specialized migration tools for Teams, recreate teams and memberships, and validate access to underlying SharePoint data. | Abort migration and remain in source tenant. |
| Licensing & Feature Gaps - Users lose access to features due to incorrect or missing license assignments in the new tenant. | Low | Map licenses ahead of time, assign before user cutover, and validate service availability (Exchange, Teams, etc.). | Abort migration and remain in source tenant. |
| Conditional Access / Security Policy Conflicts - Users get blocked by Conditional Access, MFA loops, or device compliance issues. | Medium | Review and stage Conditional Access policies, test with pilot users, and temporarily relax policies during migration if necessary. | Abort migration and remain in source tenant. |
| DNS Cutover Timing Issues - Improper timing causes downtime, mail routing issues, or service interruptions. | Low | Lower DNS Time-To-Live (TTL) well in advance, schedule cutover during low usage, and validate DNS changes immediately after cutover. | Abort migration and remain in source tenant. |
| User Confusion & Support Overload - Even if everything technically works, users flood support because things look different or require new logins. | Medium | Communicate clearly, provide quick-start guides, run pilot groups, and have hypercare support ready post-cutover. | N/A |

## Testing and Verification

The following data points will be used to verify a successful migration:

- User able to login to https://portal.office.com

- User able to open Outlook, send and receive email

- User able to view and create calendar invites

- User able to open Egnyte public and private folders

- User able to open and use Teams as expected

- User able to use Outlook on mobile device

## Next Day Support

Next Day Support Strategy:

- Support Type: Onsite & Remote
- Thrive Resource(s): Thrive project engineers, Thrive pod 
- Coverage Hours: Support bridge for immediate NDS, subsequent times per pod via support tickets
- Customer Contact: Ed Mielcarek

# Phase 6 – Clearstead Trust Workstation Entra Migration to Clearstead HQ

## Requirements/Prerequisites

- Signed and Executed Statement of Work

- Completion of Phase 1

- This phase will run concurrent with Phase 5

## Approximate Timing

This phase is expected to take approximately 3 weeks from start to finish.

## Implementation Details

Current State Overview

Clearstead Trust has a dedicated Active Directory environment running on a two host VMware HA cluster with a NetApp SAN as shared storage.  This currently consists of two domain controllers (CSTRUST-AD1 and CSTRUST-AD2), a file server (CSTRUST-FILE), and a server used for PowerChute Network Shutdown (CSTRUST-PCNS).  Additionally, VM’s exist for Arctic Wolf (replaced during onboarding) and Zerto.  There are approximately 21 workstations joined to the Clearstead Trust Active Directory.

Change Summary for Future State

Clearstead Trust workstations will be migrated to Clearstead HQ Entra.

Workstation Migrations

Workstations will be migrated to Clearstead Entra.  The high-level process for this is as follows:

- Ensure a local admin account is known and accessible

- Ensure the applicable Clearstead Trust user has a Clearstead Azure AD account and can MFA to it successfully

- Unjoin the workstation from the Clearstead Trust AD

- Entra join the workstation to the Clearstead tenant

- Sign in as the user

- Migrate the relevant files from the Clearstead Trust AD profile to the newly created Entra profile for the user

Note that Thrive will try to script Entra and domain migrations.  In the event it doesn't work, it will be necessary to join manually with user assistance, approximately 1 hour per machine.

## Risks and Mitigations

| Risk | Likelihood | Mitigation Strategy | Rollback Plan |
| --- | --- | --- | --- |
| User Profile Loss / New Profile Creation - Users log in post-migration and get a fresh profile - desktop empty, apps reset, Outlook signatures gone. | Low | Use profile migration tools and test profile continuity with pilot users before broad rollout. | Rejoin devices to Clarius AD. |
| Application Authentication Breakage - Apps tied to old domain credentials stop working (line-of-business apps, mapped drives, legacy auth apps). | Low | Inventory all apps beforehand, reconfigure apps for Entra ID, and test critical apps with pilot users. | Rejoin devices to Clarius AD. |
| Loss of Access to Network Resources - Users can’t access files, printers, or internal apps still tied to the old domain. | Medium | Migrate resources to cloud (Egnyte) or implement hybrid access. Clearly define what is being decommissioned vs. retained and where the new data lives via user comms. | Rejoin devices to Clarius AD. |
| Device Join / Enrollment Failures - Devices fail to join Microsoft Entra ID or enroll in Microsoft Intune, leaving them unmanaged. | Low | Validate join/enrollment process, ensure licensing is correct, and test across device types. | Rejoin devices to Clarius AD. |
| Conditional Access & Compliance Lockouts - Devices or users get blocked immediately after migration due to Conditional Access or compliance policies. | Low | Stage policies in report-only mode first, exclude pilot users, and gradually enforce policies after confirming device compliance. | Rejoin devices to Clarius AD. |
| GPO Loss / Configuration Drift - All Group Policy Objects disappear, and machines lose security settings, mapped drives, and configurations. | Low | Translate GPOs into Intune configuration profiles, compliance policies, and scripts. | Rejoin devices to Clarius AD. |
| Printer & Drive Mapping Failures - mapped drives and printers vanish, and users suddenly forget how to function. | Low | Ensure exhaustive end user comms. | N/A |
| Remote User Disruption - Remote users can’t authenticate or complete the migration because they’re off-network. | Medium | Use remote-friendly migration methods, ensure internet-based access to required services, and provide clear instructions. Alternatively, require user device to be in-office during migration. | Rejoin devices to Clarius AD. |
| User Experience Shock (a.k.a. “Everything Looks Different”) - Even if technically successful, users struggle with new login format, missing resources, or changed workflows. | High | Communicate clearly with exhaustive comms and run a pilot group to identify pain points before full rollout. | N/A |

## Testing and Verification

The following data points will serve to confirm a successful migration:

- Device is present in Entra

- Device shows Compliant in Intune, policies applied

- Primary user is correctly assigned

- User is able to login successfully with MFA prompts

- User expected items (desktop, documents, etc) are present

- Egnyte is usable

- Expected applications open and function

- Outlook is connected to mailbox and shows expected data

- Teams is connected and usable

- Printers are as expected and usable

- VPN profile is usable, if applicable

## Next Day Support

Next Day Support Strategy:

- Support Type: Onsite & Remote
- Thrive Resource(s): Thrive project engineers, Thrive pod
- Coverage Hours: Support bridge for immediate NDS, subsequent times per pod via support tickets
- Customer Contact: Ed Mielcarek

# Phase 7 – Clearstead Trust Server and Win11 virtual workstation Decommissioning

## Requirements/Prerequisites

- Signed and Executed Statement of Work

- Phase 5 complete

- Phase 6 complete

## Approximate Timing

This phase is expected to take approximately 3 weeks from start to finish.

## Implementation Details

Current State Overview

Clearstead Trust has a dedicated Active Directory environment running on a two host VMware HA cluster with a NetApp SAN as shared storage.  This currently consists of two domain controllers (CSTRUST-AD1 and CSTRUST-AD2), a file server (CSTRUST-FILE), and a server used for PowerChute Network Shutdown (CSTRUST-PCNS).  Additionally, VM’s exist for Arctic Wolf (replaced during onboarding) and Zerto.  There are approximately 21 workstations joined to the Clearstead Trust Active Directory.

Change Summary for Future State

All virtual servers and VMware hosts will be decommissioned, which will eliminate all servers at this entity.

Server Decommissions

The following hosts and virtual machines at will be decommissioned by Thrive:

- CSTRUST-FILE (File server)

- This server has been checked for recent files in late February.  There were a handful of recent scan files created by John Norton in the PortlandScans share.  Clearstead was notified of this at that time.

- Assuming the above is resolved, this server can be decommissioned at any time.  It will be shutdown for a period of time in advance of being decommissioned to ensure no users are still accessing it.  An archival backup of the server may be desired prior to decommissioning.

- CSTRUST-AD1 (Domain Controller)

- This server can be decommissioned subsequent to all workstations and users being migrated to Entra.  An archival backup of the server may be desired prior to decommissioning.

- CSTRUST-AD2 (Domain Controller)

- This server can be decommissioned subsequent to all workstations and users being migrated to

- CSTRUST-PCNS (PowerChute Network Shutdown server)

- This server can be decommissioned subsequent to the decommission of all servers utilizing PowerChute.  The UPS unit(s) themselves will remain in place to provide emergency power and power conditioning to the network equipment.

- AWSCANNER

- This is for the legacy Arctic Wolf security product, replaced by Thrive tools.  This can be decommissioning immediately.

- CSTRUST-ZVMA

- This server/appliance can be decommissioned once all the above virtual servers are decommissioned.

- Z-VRA-CSTRUST-ESXI1

- This server/appliance can be decommissioned once all the above virtual servers are decommissioned.

- Z-VRA-CSTRUST-ESXI2

- This server/appliance can be decommissioned once all the above virtual servers are decommissioned.

- CSTRUST-ESXI1 (ESXi host)

- This physical host server can be decommissioned after the virtual infrastructure using it has been decommissioned.

- CSTRUST-ESXI2 (ESXi host)

- This physical host server can be decommissioned after the virtual infrastructure using it has been decommissioned.

- NetApp SAN

- The NetApp SAN can be decommissioned when all the above servers are out of production.

## Risks and Mitigations

| Risk | Likelihood | Mitigation Strategy | Rollback Plan |
| --- | --- | --- | --- |
| Server still in use by users, processes or workflows. | Medium | Identify server role(s) and installed applications. Confirm no active users or business processes rely on servers. Notify application owners and business stakeholders. Obtain formal approval to decommission. Confirm replacement systems (if applicable) are fully operational. | Turn server back on. |

## Testing and Verification

The following data points will serve to confirm a successful decommission of each server and virtual workstation:

- Last backup is successful and present

- Server is removed from domain, AD object not present

- Internal DNS records for server removed

- Connectivity to replacement system, if applicable, is verified

- Server is removed from monitoring tools

- Documentation is updated reflecting removal of server/workstation

## Next Day Support

Next Day Support Strategy:

- Support Type: Remote
- Thrive Resource(s): Thrive project engineers, Thrive pod 
- Coverage Hours: Support bridge for immediate NDS, subsequent times per pod via support tickets
- Customer Contact: Ed Mielcarek

# Phase 8 – Clearstead Avalon Trust Server Migration to Clearstead HQ and Virtual Workstation Decommissioning

## Requirements/Prerequisites

- Signed and Executed Statement of Work

- This phase will run concurrent with Phase 9

- This phase will run concurrent with Phase 10

## Approximate Timing

This phase is expected to take approximately 4 weeks from start to finish.

## Implementation Details

Current State Overview

Clearstead Avalon Trust has a dedicated Active Directory environment running on a Hyper-V server utilizing local storage in the Sante Fe, NM site.  Active Directory consists of three domain controllers (AT-DC-01, AT-VMHOST-01, AT-VMHOST-02 in Ridgewood, NJ), two of which are also Hyper-V hosts.

A file server (AT-FS-01) is present that has no recently modified or accessed user files (last in 2024).  While this server was not listed on the original order as being targeted for decommission, it appears to now be unused and can potentially be decommissioned.

An application server for Quickbooks (AT-APP-01, Q: and S: drives) is in the environment.  This server also has shares/volumes for scanning (R:), Advent (V:), WMP (W:), and Tandem (X:).

VMs exists for Arctic Wolf (replaced during onboarding), and there are also 20 Windows 11 virtual desktops.

A Hyper-V server (AT-VMHOST-02) in Ridgewood, NJ is used as a Hyper-V replication target of the virtual servers in Sante Fe for the purposes of disaster recovery.

Change Summary for Future State

Servers will be joined to the Clearstead HQ Active Directory.  Virtual workstations will be replaced with laptops by the Clearstead IT team and the VM’s decommissioned by Thrive.

Windows 11 Virtual Workstation Decommissioning

20 Windows 11 virtual workstations exist for the purposes of allowing users to access the environment in the office (some via thin clients) and remotely.  Clearstead has stated the intent to provision laptops for the associated users, which would negate the need for these VM’s.  As such, migration of these VM’s to the Clearstead domain is not scoped in this Technical Implementation Plan.  Once the laptops are provisions, these VM’s will be shut down and decommissioned.

Server Migrations

Active Directory migration of servers is both simple and complicated at the same time.  Unjoining and rejoining of servers from one AD to another is a relatively simple process.  However, care must be taken to ensure that proper planning is done to account for authentication changes and how they affect the various applications and solutions in the environment.

Three (3) servers exist that are in scope to be migrated (AT-DC-01, AT-APP-01, AT-FS-01).

- AT-FS-01 has a root data folder of C:\ATDATA.  An analysis of this folder shows that there have been no files created, modified or accessed in 8 months.  While not in scope for decommission in the original order, it appears this server is abandoned and can be decommissioned.

- AT-APP-01 appears to be used solely as a file server for Advent, Quickbooks and as a scanning repository.  It does have the Quickbooks server-side component and client installed.  It can be unjoined from the Clearstead Avalon Trust domain and joined to the Clearstead domain.  The authentication for the relevant scanners will likely need to be reconfigured when this is done.

- AT-DC-01 is the domain controller for the site.  It is used for Azure AD Connect synchronization and has the Unifi controller on it.  Nothing notable beyond this was discovered.  It can be demoted from the Clearstead Avalon Trust AD and promoted into the Clearstead AD.

## Risks and Mitigations

| Risk | Likelihood | Mitigation Strategy | Rollback Plan |
| --- | --- | --- | --- |
| Server still in use by users, processes or workflows. | Medium | Identify server role(s) and installed applications. Confirm no active users or business processes rely on servers. Notify application owners and business stakeholders. Obtain formal approval to decommission. Confirm replacement systems (if applicable) are fully operational. | Turn server back on. |
| Application Authentication Breakage - Apps tied to old domain credentials stop working (line-of-business apps, mapped drives, legacy auth apps). | Low | Inventory all apps beforehand, reconfigure apps for Entra ID, and test critical apps with pilot users. | Rejoin devices to Clarius AD. |

## Testing and Verification

The following data points will serve to confirm a successful migration of each server to the Clearstead HQ Active Directory:

- Server is joined to the Clearstead HD Active Directory

- Server is accessible by end users for its intended purpose

The following data points will serve to confirm a successful decommission of each virtual workstation:

- Workstation is removed from domain, AD object not present

- Internal DNS records for workstation removed

- Documentation is updated reflecting removal of workstation

## Next Day Support

Next Day Support Strategy:

- Support Type: Remote
- Thrive Resource(s): Thrive project engineers, Thrive pod 
- Coverage Hours: Support bridge for immediate NDS, subsequent times per pod via support tickets
- Customer Contact: Ed Mielcarek

# Phase 9 – Clearstead Avalon Trust Workstation Hybrid AD Migration to HQ

## Requirements/Prerequisites

- Signed and Executed Statement of Work

- This phase will run concurrent with Phase 8

- This phase will run concurrent with Phase 10

## Approximate Timing

This phase is expected to take approximately 4 weeks from start to finish.

## Implementation Details

Current State Overview

Clearstead Avalon Trust has a dedicated Active Directory environment with approximately 11 workstations either in a workgroup or joined to the Avalon Trust Active Directory.

Change Summary for Future State

Existing workstations will be hybrid joined to the Clearstead HQ Active Directory.

Workstation Migrations

Workstations will be migrated and hybrid joined to the Clearstead Active Directory.  The high-level process for this is as follows:

- Ensure a local admin account is known and accessible

- Ensure the applicable Clearstead Avalon Trust user has a Clearstead AD account

- Unjoin the workstation from the Clearstead Avalon Trust AD

- Join the workstation to the Clearstead AD

- Join the workstation to Clearstead Entra

- Sign in as the user

- Migrate the relevant files from the Clearstead Avalon Trust AD profile to the newly created profile for the user

Windows 11 Virtual Workstations

20 Windows 11 virtual workstations exist for the purposes of allowing users to access the environment in the office (some via thin clients) and remotely.  Clearstead has stated the intent to provision laptops for the associated users, which would negate the need for these VM’s.  As such, migration of these VM’s to the Clearstead domain is not scoped in this Technical Implementation Plan.  Once the laptops are provisions, these VM’s can be shut down and decommissioned.

Server Migrations

Active Directory migration of servers is both simple and complicated at the same time.  Unjoining and rejoining of servers from one AD to another is a relatively simple process.  However, care must be taken to ensure that proper planning is done to account for authentication changes and how they affect the various applications and solutions in the environment.

Three (3) servers exist that are in scope to be migrated (AT-DC-01, AT-APP-01, AT-FS-01).

- AT-FS-01 has a root data folder of C:\ATDATA.  An analysis of this folder shows that there have been no files created, modified or accessed in 8 months.  While not in scope for decommission in the original order, it appears this server is abandoned and can be decommissioned.

- AT-APP-01 appears to be used solely as a file server for Advent, Quickbooks and as a scanning repository.  It does have the Quickbooks server-side component and client installed.  It can be unjoined from the Clearstead Avalon Trust domain and joined to the Clearstead domain.  The authentication for the relevant scanners will likely need to be reconfigured when this is done.

- AT-DC-01 is the domain controller for the site.  It is used for Azure AD Connect synchronization and has the Unifi controller on it.  Nothing notable beyond this was discovered.  It can be demoted from the Clearstead Avalon Trust AD and promoted into the Clearstead AD.  Azure AD Connect will need to be reconfigured subsequent to this if still in use.

## Risks and Mitigations

| Risk | Likelihood | Mitigation Strategy | Rollback Plan |
| --- | --- | --- | --- |
| Server still in use by users, processes or workflows. | Medium | Identify server role(s) and installed applications. Confirm no active users or business processes rely on servers. Notify application owners and business stakeholders. Obtain formal approval to decommission. Confirm replacement systems (if applicable) are fully operational. | Turn server back on. |
| User Profile Loss / New Profile Creation - Users log in post-migration and get a fresh profile - desktop empty, apps reset, Outlook signatures gone. | Low | Use profile migration tools and test profile continuity with pilot users before broad rollout. | Rejoin devices to Clarius AD. |
| Application Authentication Breakage - Apps tied to old domain credentials stop working (line-of-business apps, mapped drives, legacy auth apps). | Low | Inventory all apps beforehand, reconfigure apps for Entra ID, and test critical apps with pilot users. | Rejoin devices to Clarius AD. |
| Loss of Access to Network Resources - Users can’t access files, printers, or internal apps still tied to the old domain. | Medium | Migrate resources to cloud (Egnyte) or implement hybrid access. Clearly define what is being decommissioned vs. retained and where the new data lives via user comms. | Rejoin devices to Clarius AD. |
| Device Join / Enrollment Failures - Devices fail to join Microsoft Entra ID or enroll in Microsoft Intune, leaving them unmanaged. | Low | Validate join/enrollment process, ensure licensing is correct, and test across device types. | Rejoin devices to Clarius AD. |
| Conditional Access & Compliance Lockouts - Devices or users get blocked immediately after migration due to Conditional Access or compliance policies. | Low | Stage policies in report-only mode first, exclude pilot users, and gradually enforce policies after confirming device compliance. | Rejoin devices to Clarius AD. |
| GPO Loss / Configuration Drift - All Group Policy Objects disappear, and machines lose security settings, mapped drives, and configurations. | Low | Translate GPOs into Intune configuration profiles, compliance policies, and scripts. | Rejoin devices to Clarius AD. |
| Printer & Drive Mapping Failures - mapped drives and printers vanish, and users suddenly forget how to function. | Low | Ensure exhaustive end user comms. | N/A |
| Remote User Disruption - Remote users can’t authenticate or complete the migration because they’re off-network. | Medium | Use remote-friendly migration methods, ensure internet-based access to required services, and provide clear instructions. Alternatively, require user device to be in-office during migration. | Rejoin devices to Clarius AD. |
| User Experience Shock (a.k.a. “Everything Looks Different”) - Even if technically successful, users struggle with new login format, missing resources, or changed workflows. | High | Communicate clearly with exhaustive comms and run a pilot group to identify pain points before full rollout. | N/A |

## Testing and Verification

The following data points will serve to confirm a successful decommission of each server:

- Last backup is successful and present

- Server is removed from domain, AD object not present

- Internal DNS records for server removed

- Connectivity to replacement system, if applicable, is verified

- Server is removed from monitoring tools

- Documentation is updated reflecting removal of server

The following data points will serve to confirm a successful workstation migration:

- Device is present in Entra

- Device shows Compliant in Intune, policies applied

- Primary user is correctly assigned

- User is able to login successfully with MFA prompts

- User expected items (desktop, documents, etc) are present

- Egnyte is usable

- Expected applications open and function

- Outlook is connected to mailbox and shows expected data

- Teams is connected and usable

- Printers are as expected and usable

- VPN profile is usable, if applicable

## Next Day Support

Next Day Support Strategy:

- Support Type: Remote
- Thrive Resource(s): Thrive project engineers, Thrive pod 
- Coverage Hours: Support bridge for immediate NDS, subsequent times per pod via support tickets
- Customer Contact: Ed Mielcarek

# Phase 10 –Clearstead Avalon Trust M365 Migration

## Requirements/Prerequisites

- Signed and Executed Statement of Work

- Completion of Phase 1

- This phase will run concurrent with Phase 8

- This phase will run concurrent with Phase 9

## Approximate Timing

This phase is expected to take approximately 4 weeks from start to finish.

## Implementation Details

Current State Overview

Clearstead Avalon Trust has a dedicated M365 environment.

Change Summary for Future State

The Clearstead Avalon Trust M365 environment will be migrated to the Clearstead HQ tenant.

Data Cleanup/Archival

In advance of any M365 work as described below, it is recommended that a data cleanup/archival task be completed, led by the Clearstead IT team.  This will ensure that old and unused legacy data is not carried forward into Egnyte or from M365 tenant to tenant.

Exchange Online Migration

An M365 migration will be executed, with mailboxes and associated assets being moved to the Clearstead tenant.  There are currently approximately 26 user and 3 shared mailboxes within the Clearstead Avalon Trust tenant.  There are three 365 groups, fifteen distribution lists, no dynamic distribution lists and no mail-enabled security groups that will be migrated.  There are no resource mailboxes and 9 contacts to migrate.

There is 1 Exchange transport rule to migrate.

No public folder mailboxes exist.

M365 licensing consists of E3 and Exchange Online (Plan 1) licenses.

The third-party email security solutions Appriver is in use.  There three email connectors for routing email to Clearstead HQ and Appriver.

Accepted domains consist of the following:

- avalontrust.com (default domain)

- avalontrustsf.onmicrosoft.com

- avalontrustsf.mail.onmicrosoft.com

Any MTO currently in place will be torn down 7-14 days prior to the start of work for this migration, as mailboxes will be required to be created for the users as a target for the source tenant.

Microsoft Teams Migration

Teams is in use on a minimal basis, with only 1 channel in existence.  Thrive will migrate to the Clearstead tenant.

Sharepoint Online and OneDrive Migration

A total of 4 Sharepoint Online active sites exist with no files/space used.  There are 500-600 OneDrive files for all users total, with no user having more than 80 files using less than 1GB space.  These will be migrated to Egnyte.

## Risks and Mitigations

| Risk | Likelihood | Mitigation Strategy | Rollback Plan |
| --- | --- | --- | --- |
| Identity Mismatch / Login Failures - Users can’t log in, duplicate accounts appear, or SSO breaks due to mismatched UPNs or other account settings. | Medium | Validate authentication with a pilot group. | Abort migration and remain in source tenant. |
| Mail Flow Disruption - Emails bounce, disappear, or route incorrectly. | Low | Lower DNS TTL in advance, validate connectors and routing rules, and perform cutover testing as detailed below. | Abort migration and remain in source tenant. |
| File Access/Availability Issues - Mailboxes, OneDrive, or SharePoint data fails to fully migrate, or items are skipped without visibility. | Low | Run pre-migration assessments, use reputable migration tools, review error reports in detail, and perform post-migration validation as detailed below. | Abort migration and remain in source tenant. |
| Outlook & Client Issues - Users get constant password prompts, Outlook profiles break, or Autodiscover points to the wrong tenant. | Low | Plan for Outlook profile rebuild or use tools/scripts to reset same, clear cached credentials, and ensure DNS/Autodiscover cutover is tightly coordinated. | Abort migration and remain in source tenant. |
| Application & SSO Failures - Line-of-business apps and third-party integrations stop working due to tenant change or missing enterprise app configs. | Low | Inventory all applications using Azure AD, reconfigure enterprise apps in target tenant, test SSO thoroughly, and validate SCIM/provisioning where used. | Abort migration and remain in source tenant. |
| Teams & Collaboration Gaps - Loss of chat history, broken Teams memberships, missing files, or degraded collaboration experience. | Medium | Set expectations (chat history often limited), use specialized migration tools for Teams, recreate teams and memberships, and validate access to underlying SharePoint data. | Abort migration and remain in source tenant. |
| Licensing & Feature Gaps - Users lose access to features due to incorrect or missing license assignments in the new tenant. | Low | Map licenses ahead of time, assign before user cutover, and validate service availability (Exchange, Teams, etc.). | Abort migration and remain in source tenant. |
| Conditional Access / Security Policy Conflicts - Users get blocked by Conditional Access, MFA loops, or device compliance issues. | Medium | Review and stage Conditional Access policies, test with pilot users, and temporarily relax policies during migration if necessary. | Abort migration and remain in source tenant. |
| DNS Cutover Timing Issues - Improper timing causes downtime, mail routing issues, or service interruptions. | Low | Lower DNS Time-To-Live (TTL) well in advance, schedule cutover during low usage, and validate DNS changes immediately after cutover. | Abort migration and remain in source tenant. |
| User Confusion & Support Overload - Even if everything technically works, users flood support because things look different or require new logins. | Medium | Communicate clearly, provide quick-start guides, run pilot groups, and have hypercare support ready post-cutover. | N/A |

## Testing and Verification

The following data points will be used to verify a successful migration:

- User able to login to https://portal.office.com

- User able to open Outlook, send and receive email

- User able to view and create calendar invites

- User able to open Egnyte public and private folders

- User able to open and use Teams as expected

- User able to use Outlook on mobile device

## Next Day Support

Next Day Support Strategy:

- Support Type: Onsite & Remote
- Thrive Resource(s): Thrive project engineers, Thrive pod 
- Coverage Hours: Support bridge for immediate NDS, subsequent times per pod via support tickets
- Customer Contact: Ed Mielcarek

# Phase 11 – Clearstead Advisory SOlutions Server AD Migration and Workstation Hybrid AD Migration to Clearstead HQ

## Requirements/Prerequisites

- Signed and Executed Statement of Work

- This phase will run concurrent with Phase 12

## Approximate Timing

This phase is expected to take approximately 4 weeks from start to finish.

## Implementation Details

Current State Overview

Clearstead Advisory Solutions has a dedicated Active Directory environment running in a Hyper-V ecosystem all utilizing local storage in three sites (Norfolk, VA, Raleigh, NC and Roanoke, VA) as well as a MSP owned DR center in Greensborough, NC.  This consists of 5 domain controllers, 2 in Norfolk (WST-NORF-AD-01 & WST-NORF-AD-03), 1 in Raleigh (WST-RAL-AD-01), 1 in Roanoke (WST-ROA-AD-01) and 1 at the DR site (WST-DR-AD-01).

The are 7 Hyper-V host servers in Norfolk, all with local storage, with 2 of those functioning in a Hyper-V replication target to and from the other Hyper-V servers and the DR server.

Raleigh has 2 Hyper-V hosts utilizing local storage.

Roanoke has 2 Hyper-V hosts utilizing local storage.

Norfolk has two servers dedicated to Advent (CS-NORF-APX25 & CS-NORF-SQL-25).

A server for file sharing and printing exists (WST-NORF-FS-01).

There is an application server (WST-NORF-APP-04) that houses the RedBlack app, associated SQL server and is used as the Salesforce data warehouse.

A server noted as a “future CAS print server” (CS-NORF-PRT-01) is in the environment.

There are 11 Linux servers in existence in the following roles:

KALI: Used for penetration testing

WST-NORF-APP-03: Eventlog and syslog archiver

WST-NORF-CRT-02: Certificate Authority for all external certs (“TLS and VPN”)

WST-NORF-PTL-01: sFTP destination for Broadridge, FactSet and Orion, and Automation server for nightly processes

WST-NORF-RAD-02: RADIUS server that provides AD+MFA authentication for Norfolk firewall and VPN logins


The remaining Linux servers are used for the Security Onion security solution:

WST-NORF-FIN-01: Security Onion Honeypot

CAS-NORF-SOS-MGR: Security Onion Manager

WST-NORF-SEC-01: On-prem vulnerability assessment for agentless scanning

WST-NORF-SEC-03: Sof-ELK community software – ElasticSearch/Logstash/Kibana

CAS-NORF-SOS-SN1: Security Onion Sensor 1

CAS-NORF-SOS-SR1: Security Onion Search (Elastic Search)

There are 4 virtual workstations (VWORKSTATION-01, VWORKSTATION-02, VWORKSTATION-04 and VWORKSTATION-05) for IT management, Marketing, Legal, and Trading respectively.  

Lastly, there are approximately 68 user workstations that will be hybrid joined to the Clearstead Entra/HQ Active Directory.

Change Summary for Future State

Clearstead Advisory Solutions servers and virtual workstations will be migrated to the Clearstead HQ Active Directory.

Active Directory Server and Virtual Workstation Migration

Active Directory migration of servers is both simple and complicated at the same time.  Unjoining and rejoining of servers from one AD to another is a relatively simple process.  However, care must be taken to ensure that proper planning is done to account for authentication changes and how they affect the various applications and solutions in the environment.

The 18 servers and workstations below will be joined to, or remain in, the Clearstead Active Directory:

- WST-NORF-AD-01 is one of two domain controllers in the Norfolk site.  It currently holds all the FSMO roles.  Nothing notable was discovered on this server.  It can be demoted from the Clearstead Advisory Solutions AD and promoted into the Clearstead AD.

- WST-NORF-AD-03 is the second domain controller in the Norfolk site.  It is used for Azure AD Connect synchronization and has the Unifi controller on it.  Nothing notable beyond this was discovered.  It can be demoted from the Clearstead Avalon Trust AD and promoted into the Clearstead AD.  Azure AD Connect will need to be reconfigured subsequent to this if still in use.

- WST-RAL-AD-01 is the single domain controller in the Raleigh site.  It also is used to share 4 printers.  Nothing notable beyond this was discovered.  It can be demoted from the Clearstead Advisory Solutions AD and promoted into the Clearstead AD.  Printer connections may need to be re-added on workstations.

- WST-ROA-AD-01 is the single domain controller in the Roanoke site.  It also is used to share 4 printers.  Nothing notable beyond this was discovered.  It can be demoted from the Clearstead Advisory Solutions AD and promoted into the Clearstead AD.  Printer connections may need to be re-added on workstations.

- CS-NORF-APX-25 is used for the Advent Portfolio Exchange application and is already joined to Clearstead AD.  No action is needed for this server.

- CS-NORF-SQL-25 is used for the Advent Portfolio Exchange application as a SQL server and is already joined to Clearstead AD.  No action is needed for this server.

- WST-NORF-FS-01 is a file server for CAS.  It also shares 5 printers.  It is primarily used as a file repository for various automated processes and as a scanning target.  It can be demoted from the Clearstead Advisory Solutions AD and promoted into the Clearstead AD.  Printer connections may need to be re-added on workstations.  Care must be taken to ensure the various devices and solutions that write to the file shares can continue to do so subsequent to the AD migration:

Prior to migrating this server, Thrive will need to understand what apps and solutions use the above (non-Windows specific) shares.

- VWORKSTATION-01 is a remote workstation for IT management.  It can be unjoined from the Clearstead Advisory Solutions AD and joined into the Clearstead AD.

- VWORKSTATION-02 is a remote workstation for Marketing.  It can be unjoined from the Clearstead Advisory Solutions AD and joined into the Clearstead AD.

- VWORKSTATION-04 is a remote workstation for legal compliance officer.  It can be unjoined from the Clearstead Advisory Solutions AD and joined into the Clearstead AD.

- VWORKSTATION-05 is a remote workstation for Trading.  It can be unjoined from the Clearstead Advisory Solutions AD and joined into the Clearstead AD.

- WST-NORF-CRT-02 is a Linux server used as a Certificate Authority for all external use certs, TLS and VPN.  As a Linux server, it is not domain joined and no action is necessary for this server.

- WST-NORF-PTL-01 is a Linux server used as an sFTP destination for Broadridge, FactSet and Orion, Automation Server for Nightly Processes.  As a Linux server, it is not domain joined and no action is necessary for this server.

- WST-NORF-RAD-02 is a Linux server with the purpose of providing RADIUS AD+MFA authentication for Norfolk Firewall and VPN Logins.  As a Linux server, it is not domain joined and no action is necessary for this server.

- WST-NORF-APP-04 is an application server for the RedBlack application and associated SQL Server as well as a Salesforce Data Warehouse SQL Server.  While it can be unjoined from the Clearstead Advisory Solutions AD and joined into the Clearstead AD, careful planning will need to be done to assure the noted solutions can still be used subsequent to the AD migration.

- CS-NORF-PRT-01 is a print server and is already joined to Clearstead AD.  No action is needed for this server.

- WST-RAL-HV-02 is a Hyper-V host.  It can be unjoined from the Clearstead Advisory Solutions AD and joined into the Clearstead AD.

- WST-NORF-HV-10 is a Hyper-V host.  It can be unjoined from the Clearstead Advisory Solutions AD and joined into the Clearstead AD.

- WST-NORF-HV-11 is a Hyper-V host.  It can be unjoined from the Clearstead Advisory Solutions AD and joined into the Clearstead AD.

## Risks and Mitigations

| Risk | Likelihood | Mitigation Strategy | Rollback Plan |
| --- | --- | --- | --- |
| Server still in use by users, processes or workflows. | Medium | Identify server role(s) and installed applications. Confirm no active users or business processes rely on servers. Notify application owners and business stakeholders. Obtain formal approval to decommission. Confirm replacement systems (if applicable) are fully operational. | Turn server back on. |
| User Profile Loss / New Profile Creation - Users log in post-migration and get a fresh profile - desktop empty, apps reset, Outlook signatures gone. | Low | Use profile migration tools and test profile continuity with pilot users before broad rollout. | Rejoin devices to Clarius AD. |
| Application Authentication Breakage - Apps tied to old domain credentials stop working (line-of-business apps, mapped drives, legacy auth apps). | Low | Inventory all apps beforehand, reconfigure apps for Entra ID, and test critical apps with pilot users. | Rejoin devices to Clarius AD. |
| Loss of Access to Network Resources - Users can’t access files, printers, or internal apps still tied to the old domain. | Medium | Migrate resources to cloud (Egnyte) or implement hybrid access. Clearly define what is being decommissioned vs. retained and where the new data lives via user comms. | Rejoin devices to Clarius AD. |
| Device Join / Enrollment Failures - Devices fail to join Microsoft Entra ID or enroll in Microsoft Intune, leaving them unmanaged. | Low | Validate join/enrollment process, ensure licensing is correct, and test across device types. | Rejoin devices to Clarius AD. |
| Conditional Access & Compliance Lockouts - Devices or users get blocked immediately after migration due to Conditional Access or compliance policies. | Low | Stage policies in report-only mode first, exclude pilot users, and gradually enforce policies after confirming device compliance. | Rejoin devices to Clarius AD. |
| GPO Loss / Configuration Drift - All Group Policy Objects disappear, and machines lose security settings, mapped drives, and configurations. | Low | Translate GPOs into Intune configuration profiles, compliance policies, and scripts. | Rejoin devices to Clarius AD. |
| Printer & Drive Mapping Failures - mapped drives and printers vanish, and users suddenly forget how to function. | Low | Ensure exhaustive end user comms. | N/A |
| Remote User Disruption - Remote users can’t authenticate or complete the migration because they’re off-network. | Medium | Use remote-friendly migration methods, ensure internet-based access to required services, and provide clear instructions. Alternatively, require user device to be in-office during migration. | Rejoin devices to Clarius AD. |
| User Experience Shock (a.k.a. “Everything Looks Different”) - Even if technically successful, users struggle with new login format, missing resources, or changed workflows. | High | Communicate clearly with exhaustive comms and run a pilot group to identify pain points before full rollout. | N/A |

## Testing and Verification

The following data points will serve to confirm a successful decommission of each server:

- Last backup is successful and present

- Server is removed from domain, AD object not present

- Internal DNS records for server removed

- Connectivity to replacement system, if applicable, is verified

- Server is removed from monitoring tools

- Documentation is updated reflecting removal of server

## Next Day Support

Next Day Support Strategy:

- Support Type: Remote
- Thrive Resource(s): Thrive project engineers, Thrive pod 
- Coverage Hours: Support bridge for immediate NDS, subsequent times per pod via support tickets
- Customer Contact: Ed Mielcarek

# Phase 12 – Clearstead Advisory SOlutions Workstation Hybrid Migrations To ClearStead HQ

## Requirements/Prerequisites

- Signed and Executed Statement of Work

- This phase will run concurrent with Phase 11

## Approximate Timing

This phase is expected to take approximately 3 weeks from start to finish.

## Implementation Details

Current State Overview

There are approximately 68 user workstations present in the Clearstead Advisory Solutions Active Directory environment.

Change Summary for Future State

Clearstead Advisory Solutions servers and virtual workstations will be migrated and hybrid joined to the Clearstead HQ Active Directory.

Workstation Migrations

Approximately 68 workstations will be migrated to the Clearstead Active Directory and hybrid Entra joined to the Clearstead HQ tenant.  The high-level process for this is as follows:

- Ensure a local admin account is known and accessible

- Ensure the applicable Clearstead Avalon Trust user has a Clearstead AD account

- Unjoin the workstation from the Clearstead Avalon Trust AD

- Join the workstation to the Clearstead AD

- Entra join the workstation

- Sign in as the user

- Migrate the relevant files from the Clearstead Avalon Trust AD profile to the newly created profile for the user

Note that Thrive will try to script Entra and domain migrations.  In the event it doesn't work, it will be necessary to join manually with user assistance, approximately 1 hour per machine.

## Risks and Mitigations

| Risk | Likelihood | Mitigation Strategy | Rollback Plan |
| --- | --- | --- | --- |
| Server still in use by users, processes or workflows. | Medium | Identify server role(s) and installed applications. Confirm no active users or business processes rely on servers. Notify application owners and business stakeholders. Obtain formal approval to decommission. Confirm replacement systems (if applicable) are fully operational. | Turn server back on. |
| User Profile Loss / New Profile Creation - Users log in post-migration and get a fresh profile - desktop empty, apps reset, Outlook signatures gone. | Low | Use profile migration tools and test profile continuity with pilot users before broad rollout. | Rejoin devices to Clarius AD. |
| Application Authentication Breakage - Apps tied to old domain credentials stop working (line-of-business apps, mapped drives, legacy auth apps). | Low | Inventory all apps beforehand, reconfigure apps for Entra ID, and test critical apps with pilot users. | Rejoin devices to Clarius AD. |
| Loss of Access to Network Resources - Users can’t access files, printers, or internal apps still tied to the old domain. | Medium | Migrate resources to cloud (Egnyte) or implement hybrid access. Clearly define what is being decommissioned vs. retained and where the new data lives via user comms. | Rejoin devices to Clarius AD. |
| Device Join / Enrollment Failures - Devices fail to join Microsoft Entra ID or enroll in Microsoft Intune, leaving them unmanaged. | Low | Validate join/enrollment process, ensure licensing is correct, and test across device types. | Rejoin devices to Clarius AD. |
| Conditional Access & Compliance Lockouts - Devices or users get blocked immediately after migration due to Conditional Access or compliance policies. | Low | Stage policies in report-only mode first, exclude pilot users, and gradually enforce policies after confirming device compliance. | Rejoin devices to Clarius AD. |
| GPO Loss / Configuration Drift - All Group Policy Objects disappear, and machines lose security settings, mapped drives, and configurations. | Low | Translate GPOs into Intune configuration profiles, compliance policies, and scripts. | Rejoin devices to Clarius AD. |
| Printer & Drive Mapping Failures - mapped drives and printers vanish, and users suddenly forget how to function. | Low | Ensure exhaustive end user comms. | N/A |
| Remote User Disruption - Remote users can’t authenticate or complete the migration because they’re off-network. | Medium | Use remote-friendly migration methods, ensure internet-based access to required services, and provide clear instructions. Alternatively, require user device to be in-office during migration. | Rejoin devices to Clarius AD. |
| User Experience Shock (a.k.a. “Everything Looks Different”) - Even if technically successful, users struggle with new login format, missing resources, or changed workflows. | High | Communicate clearly with exhaustive comms and run a pilot group to identify pain points before full rollout. | N/A |

## Testing and Verification

The following data points will serve to confirm a successful workstation migration:

- Device is present in Entra

- Device shows Compliant in Intune, policies applied

- Primary user is correctly assigned

- User is able to login successfully with MFA prompts

- User expected items (desktop, documents, etc) are present

- Egnyte is usable

- Expected applications open and function

- Outlook is connected to mailbox and shows expected data

- Teams is connected and usable

- Printers are as expected and usable

- VPN profile is usable, if applicable

## Next Day Support

Next Day Support Strategy:

- Support Type: Remote
- Thrive Resource(s): Thrive project engineers, Thrive pod 
- Coverage Hours: Support bridge for immediate NDS, subsequent times per pod via support tickets
- Customer Contact: Ed Mielcarek

# Phase 13 – Clearstead Advisory Solutions Server Decommissioning

## Requirements/Prerequisites

- Signed and Executed Statement of Work

- This phase will run concurrent with Phase 11

- This phase will run concurrent with Phase 12

## Approximate Timing

This phase is expected to take approximately 3 weeks from start to finish.

## Implementation Details

Current State Overview

Clearstead Advisory Solutions has a dedicated Active Directory environment running in a Hyper-V ecosystem all utilizing local storage in three sites (Norfolk, VA, Raleigh, NC and Roanoke, VA) as well as a MSP owned DR center in Greensborough, NC.  This consists of 5 domain controllers, 2 in Norfolk (WST-NORF-AD-01 & WST-NORF-AD-03), 1 in Raleigh (WST-RAL-AD-01), 1 in Roanoke (WST-ROA-AD-01) and 1 at the DR site (WST-DR-AD-01).

The are 7 Hyper-V host servers in Norfolk, all with local storage, with 2 of those functioning in a Hyper-V replication target to and from the other Hyper-V servers and the DR server.

Raleigh has 2 Hyper-V hosts utilizing local storage.

Roanoke has 2 Hyper-V hosts utilizing local storage.

Norfolk has two servers dedicated to Advent (CS-NORF-APX25 & CS-NORF-SQL-25).

A server for file sharing and printing exists (WST-NORF-FS-01).

There is an application server (WST-NORF-APP-04) that houses the RedBlack app, associated SQL server and is used as the Salesforce data warehouse.

A server noted as a “future CAS print server” (CS-NORF-PRT-01) is in the environment.

There are 11 Linux servers in existence in the following roles:

KALI: Used for penetration testing

WST-NORF-APP-03: Eventlog and syslog archiver

WST-NORF-CRT-02: Certificate Authority for all external certs (“TLS and VPN”)

WST-NORF-PTL-01: sFTP destination for Broadridge, FactSet and Orion, and Automation server for nightly processes

WST-NORF-RAD-02: RADIUS server that provides AD+MFA authentication for Norfolk firewall and VPN logins


The remaining Linux servers are used for the Security Onion security solution:

WST-NORF-FIN-01: Security Onion Honeypot

CAS-NORF-SOS-MGR: Security Onion Manager

WST-NORF-SEC-01: On-prem vulnerability assessment for agentless scanning

WST-NORF-SEC-03: Sof-ELK community software – ElasticSearch/Logstash/Kibana

CAS-NORF-SOS-SN1: Security Onion Sensor 1

CAS-NORF-SOS-SR1: Security Onion Search (Elastic Search)

There are 4 virtual workstations (VWORKSTATION-01, VWORKSTATION-02, VWORKSTATION-04 and VWORKSTATION-05) for IT management, Marketing, Legal, and Trading respectively.

Change Summary for Future State

Nineteen servers will be decommissioned.

Server Decommissions

The following hosts and VM's will be decommissioned:

- WST-NORF-APP-03 is a Linux server with the purpose of archiving Eventlog and Syslog data.  Prior to decommissioning this server, existing eventlog and syslog data will be preserved for compliancy purposes via a backup/archive of some kind.

- WST-NORF-FIN-01 is a Linux server used as a Security Onion honeypot.  Security Onion will be replaced with Thrive provided security tools.  This server can be decommissioned.

- WST-NORF-SEC-03 is a Linux server for Sof-ELK community software - ElasticSearch/Logstash/Kibana, which is a forensic analysis tool.  Security tools will be replaced with Thrive provided security tools.  This server can be decommissioned.

- CAS-NORF-SOS-SN1 is a Linux server used as a Security Onion sensor.  Security Onion will be replaced with Thrive provided security tools.  This server can be decommissioned.

- CAS-NORF-SOS-SR1 is a Linux server used for Security Onion elastic search.  Security Onion will be replaced with Thrive provided security tools.  This server can be decommissioned.

- CAS-NORF-SOS-MGR is a Linux server used as for a Security Onion Manager.  Security Onion will be replaced with Thrive provided security tools.  This server can be decommissioned.

- WST-NORF-SEC-01 is a Linux server for on-prem vulnerability assessment for agentless scanning.  This is replaced by Thrive-provided solutions.  This server can be decommissioned.

- KALI is a Linux server used for penetration testing.  This is replaced by Thrive-provided security toolsets.  This server can be decommissioned.

- CAS-RAL-SOS-SN1 is a Linux server used as a Security Onion sensor.  Security Onion will be replaced with Thrive provided security tools.  This server can be decommissioned.

- WST-RAL-SEC-01 is a Linux server for on-prem vulnerability assessment for agentless scanning.  This is replaced by Thrive-provided solutions.  This server can be decommissioned.

- CAS-ROA-SOS-SN1 is a Linux server used as a Security Onion sensor.  Security Onion will be replaced with Thrive provided security tools.  This server can be decommissioned.

- WST-ROA-SEC-01 is a Linux server for on-prem vulnerability assessment for agentless scanning.  This is replaced by Thrive-provided solutions.  This server can be decommissioned.

- WST-NORF-HV-01 is a Hyper-V host server.  This server can be decommissioned once all VM’s residing on it have been decommissioned.

- WST-NORF-HV-02 is a Hyper-V host server.  This server can be decommissioned once all VM’s residing on it have been decommissioned.

- WST-NORF-HV-03 is a Hyper-V host server.  This server can be decommissioned once all VM’s residing on it have been decommissioned.

- WST-NORF-HV-04 is a Hyper-V host server.  This server can be decommissioned once all VM’s residing on it have been decommissioned.

- WST-NORF-HV-05 is a Hyper-V host server.  This server can be decommissioned once all VM’s residing on it have been decommissioned.

- WST-ROA-HV-01 is a Hyper-V host server.  This server can be decommissioned once all VM’s residing on it have been decommissioned.

- WST-DR-HV-01 is a Hyper-V host server.  This server can be decommissioned once all VM’s residing on it have been decommissioned.

All servers will be shut down for several days to a week prior to decommissioning to ensure no unintended impacts.  Backups/archival copies will be taken of critical servers where concern exists for data compliance or long-term possible need.

Hyper-V DR Replication

Currently there are two Hyper-V hosts (WST-DR-HV-01 and WST-DR-HV-10) residing in the Greensborough DR Center.  The DR center rack space is leased by Clearstead, and Clearstead also owns the hardware.  WST-DR-HV-01 is noted to be decommissioned above.

WST-DR-HV-10 is used as a replication target for several Norfolk virtual servers.  

Nothing will change here during this project.

## Risks and Mitigations

| Risk | Likelihood | Mitigation Strategy | Rollback Plan |
| --- | --- | --- | --- |
| Server still in use by users, processes or workflows. | Medium | Identify server role(s) and installed applications. Confirm no active users or business processes rely on servers. Notify application owners and business stakeholders. Obtain formal approval to decommission. Confirm replacement systems (if applicable) are fully operational. | Turn server back on. |

## Testing and Verification

The following data points will serve to confirm a successful decommission of each server:

- Last backup is successful and present

- Server is removed from domain, AD object not present

- Internal DNS records for server removed

- Connectivity to replacement system, if applicable, is verified

- Server is removed from monitoring tools

- Documentation is updated reflecting removal of server

## Next Day Support

Next Day Support Strategy:

- Support Type: Remote
- Thrive Resource(s): Thrive project engineers, Thrive pod 
- Coverage Hours: Support bridge for immediate NDS, subsequent times per pod via support tickets
- Customer Contact: Ed Mielcarek

# Acceptance Criteria

The following criteria must be met before this project is considered complete:

| # | Acceptance Criterion | Verification Method |
| --- | --- | --- |
| 1 | All phases completed per this document. | Sign-off from customer project lead. |
| 2 | All servers, workstation and users successfully migrated. | Sign-off from customer project lead. |
| 3 | All critical systems accessible post-migration. | Sign-off from customer project lead. |
| 4 | No outstanding P1/P2 incidents related to migration. | Helpdesk ticket review at close. |
| 6 | Relevant documentation delivered to customer. | Documention delivery confirmation from customer project lead. |

# Deliverables

| # | Deliverable | Description | Expected Date |
| --- | --- | --- | --- |
| 1 | Technical Implementation Plan (This Document) | Scoped and signed TIP covering all phases of the project |  |
| 2 | Infrastructure Diagram | Principal Architect authored Infrastructure Diagram |  |

# Document End

This document represents the agreed scope and plan for the engagement between Thrive and Clearstead Advisors, LLC. Any changes to scope must be formally agreed upon via a Change Order and this document updated accordingly.